## ReadMe
Daily Scrum Meeting
Is held in daily morning (in IT industry)
Spends around 15 minutes (in IT industry)
This course adjusts it to WeeklyScrumReport and it need to be held at weekend.
Sprint Planing is held before starting a sprint. We need to clarify to-be-determined (TBD) tasks as follow:
Refine task priority
Size task point
Assign todo task to sprint
Assign task to member
In the other words, eventually, we'd like to clarify tasks for the upcoming sprint: (task, priority, point, who is assigned to, status)
| If we'd like to use an alternative tool like Trello instead of the provided sheet, we need to take a screenshort for each sprint planing and paste it to the corresponding sheet | https://www.youtube.com/watch?v=xky48zyL9iA
https://www.youtube.com/watch?v=cD8gryFZvLo&list=PL3Bp9JDvkArbbb4KVB_Lk9QRGohSKt9hM&index=3
Sprint Retrospective Meeting
Is held after Sprint Planing (in IT industry)
Spend around 1 hour (in IT industry)
This course adjusts it to SprintRetrospectiveReport and it need to be reported at every other weekend.
| If we'd like use an alternative tool like easyretro for the meeting instead of the provided sheet, we need to take a screenshot and paste it to the corresponding sheet | https://easyretro.io/_nuxt/img/feature3.35fd8b3.gif

## SimpleSprintPlaning
Task Id | Task Name | Priority | Point (Fibonaci value) | Sprint | Assigned to | Status
1 | Implement login page | Low | 1 | Week_11_12 | httthanh | Todo
2 | Implement signup page | Medium | 3 | Week_13_14 | httthanh | Todo
3 | Implement Creating a new Item[X] | High | 5 | Week_15_16 | httthanh | Todo
4 | Implement Reading Item[X] details | Medium | 8 | Week_11_12 | taduy | InProgress
5 | Implement Updating an existing Item[X] | Medium | 1 | Week_13_14 | taduy | Todo
6 | Implement Delete an existing Item[X] | High | 3 | Week_15_16 | taduy | Todo
7 | Implement Listing Items[X] | High | 5 | Week_11_12 | ntan | Completed
8 | Implement Searching Items[X] | Medium | 8 | Week_13_14 | ntan | Todo
9 | Implement Creating a new Item[Y] | High | 5 | Week_15_16 | ntan | Todo
10 | Implement Reading Item[Y] details | Low | 8 | Week_11_12 | httthanh | Completed
11 | Implement Updating an existing Item[Y] | Medium | 1 | Week_13_14 | httthanh | Todo
12 | Implement Delete an existing Item[Y] | High | 3 | Week_15_16 | httthanh | Todo
13 | Implement Listing Items[Y] | Medium | 5 | Week_11_12 | taduy | Todo
14 | Implement Searching Items[Y] | Medium | 8 | Week_13_14 | taduy | Todo
15 | Add Search Criteria[A] to Searching Items[X] | High | 1 | Week_15_16 | taduy | Todo
16 | Allow user to reset password via email | High | 3 | Week_11_12 | ntan | InProgress
17 | Deploy app to Heroku | Medium | 5 | Week_13_14 | ntan | Todo
18 | Make video demo for page a, b, c | High | 8 | Week_15_16 | ntan | Todo
19 | ... | TBD | TBD | TBD | TBD | Todo
20 | ... | TBD | TBD | TBD | TBD | Todo
21 | ... | TBD | TBD | TBD | TBD | Todo
22 | ... | TBD | TBD | TBD | TBD | Todo
23 | ... | TBD | TBD | TBD | TBD | Todo
24 | ... | TBD | TBD | TBD | TBD | Todo

## WeeklyScrumReport
Group | XY
Project | Project Name
Mebmer Id | Team Member | Question | End of Week 11 | End of Week 12 | End of Week 13 | End of Week 14 | End of Week 15 | End of Week 16
[Student Id] | [Name] | 1. What did you do last week? | - I finished on Task 1 relating to splash page - I worked on Task 2 relating to login page
|  | 2. What are doing this upcoming week? | - I'm finalizing Task 2. - I would take Task 3 relating to signup page
|  | 3. Is there anything blocking you? | - Need help from [Name] to provide login API exception response and status code so that I could handle errors. - Need to discuss with [Name] about the UX experience on signup page.
[Student Id] | [Name] | 1. What did you do last week?
2. What are doing this upcoming week?
3. Is there anything blocking you?
[Student Id] | [Name] | 1. What did you do last week?
2. What are doing this upcoming week?
3. Is there anything blocking you?
[Student Id] | [Name] | 1. What did you do last week?
2. What are doing this upcoming week?
3. Is there anything blocking you?
[Student Id] | [Name] | 1. What did you do last week?
2. What are doing this upcoming week?
3. Is there anything blocking you?

## SprintRetrospectiveReport
Group | XY
Project | Project Name
End of Sprint | Questions | Anonymous Person
End of Week 12 | 1. What went well? | - Each member give 1 - 2 ideas. - -
| 2. What to improve? | - Each member give 1 - 2 ideas. - -
| 3. Action item? | - Team decide at least 2 actions needed for improvements - -
End of Week 14 | 1. What went well? | - - -
| 2. What to improve? | - - -
| 3. Action item? | - - -
End of Week 16 | 1. What went well? | - - -
| 2. What to improve? | - - -
| 3. Action item? | - - -