## ReadMe
Daily Scrum Meeting
Is held in daily morning (in IT industry)
Spends around 15 minutes (in IT industry)
This course adjusts it to WeeklyScrumReport and it need to be held at weekend.
Sprint Planing is held before starting a sprint. We need to clarify to-be-determined (TBD) tasks as follow:
Refine task priority
Size task point
Assign todo task to sprint
Assign task to member
In the other words, eventually, we'd like to clarify tasks for the upcoming sprint: (task, priority, point, who is assigned to, status)
| If we'd like to use an alternative tool like Trello instead of the provided sheet, we need to take a screenshort for each sprint planing and paste it to the corresponding sheet | https://www.youtube.com/watch?v=xky48zyL9iA
https://www.youtube.com/watch?v=cD8gryFZvLo&list=PL3Bp9JDvkArbbb4KVB_Lk9QRGohSKt9hM&index=3
Sprint Retrospective Meeting
Is held after Sprint Planing (in IT industry)
Spend around 1 hour (in IT industry)
This course adjusts it to SprintRetrospectiveReport and it need to be reported at every other weekend.
| If we'd like use an alternative tool like easyretro for the meeting instead of the provided sheet, we need to take a screenshot and paste it to the corresponding sheet | https://easyretro.io/_nuxt/img/feature3.35fd8b3.gif

## SimpleSprintPlaning
Task Id | Task Name | Priority | Point (Fibonaci value) | Sprint | Assigned to | Status
1 | Vẽ Mockup các màn hình | Low | 2 | Week_11_12 | ctkhiet | Completed
2 | Thiết kế component cho Report use case | High | 7 | Week_11_12 | hdlam, ttkiet | InProgress
3 | Thiết kế kiến trúc Web App | Medium | 5 | Week_11_12 | ctkhiet | Todo
4 | Thiết kế subsystem cho Report use case | High | 7 | Week_11_12 | ndhuy, vqlam | InProgress
5 | Thiết kế ERD ở mức vật lý | Medium | 3 | Week_11_12 | hdlam | Completed
6 | Viết báo cáo Scrum | High | 3 | Week_11_12 | ctkhiet, vqlam | InProgress
7 | Vẽ Sequence Diagram cho Process / Behaviour View | Medium | 5 | Week_11_12 | ndhuy | InProgress
8 |  | TBD | TBD | TBD | TBD | Todo
9 |  | TBD | TBD | TBD | TBD | Todo
10 |  | TBD | TBD | TBD | TBD | Todo
11 |  | TBD | TBD | TBD | TBD | Todo
12
13
14
15
16
17
18
19
20
21
22
23
24

## WeeklyScrumReport
Group | 15
Project | Quản lý khách sạn
Mebmer Id | Team Member | Question | End of Week 11 | End of Week 12 | End of Week 13 | End of Week 14 | End of Week 15 | End of Week 16
19120544 | Cao Thanh Khiết | 1. What did you do last week? | - Đã vẽ xong 5 màn hình Mockup. Chia việc xong cho các thành viên | - Vẽ xong thiết kế kiến trúc cho Webapp. Tạo report hàng tuần Scrum
|  | 2. What are doing this upcoming week? | - Tìm hiểu về thiết kế kiến trúc Web Application. Tìm hiểu về báo cáo theo Scrum | - Tạo khung sườn Reactjs project cho các thành viên với các cấu hình cơ bản
3. Is there anything blocking you?
19120559 | Hà Duy Lãm | 1. What did you do last week? | - Thiết kế cơ sở dữ liệu ở mức quan niệm, tìm hiểu nghiệp vụ của project | - Đã hoàn thành thiết kế Physical ERD có kiểu dữ liệu và ràng buộc khóa
|  | 2. What are doing this upcoming week? | -Thiết kế cơ sở dữ liệu lên mức logic và physical
3. Is there anything blocking you?
19120533 | Ninh Duy Huy | 1. What did you do last week? | - Vẽ Sequence Diagram
|  | 2. What are doing this upcoming week? | - thiết kế component diagram
3. Is there anything blocking you?
19120557 | Trần Tuấn Kiệt | 1. What did you do last week? | tập hợp các component diagram đã làm ở bước UC Design | Gom nhóm các interface, implementation đã làm ở UC Design (component) vào các package
|  | 2. What are doing this upcoming week? | tập hợp các package diagram đã làm ở bước VPOC, chuẩn bị thêm interface, implementation
3. Is there anything blocking you?
19120558 | Văn Quý Lâm | 1. What did you do last week? | - Vẽ class diagram cho Booking Room Use Case
|  | 2. What are doing this upcoming week? | - Vẽ componnent diagram cho Booking Room Use Case
3. Is there anything blocking you?

## SprintRetrospectiveReport
Group | 15
Project | Quản lý khách sạn
End of Sprint | Questions | Anonymous Person
End of Week 12 | 1. What went well? | - Các thành viên đều hoàn thành đúng hạn - Họp nhóm đầy đủ, đồng ý về công việc đã phân chia -
| 2. What to improve? | - Thiết kế Use case chưa thật sự chi tiết, còn khá sơ sài - -
| 3. Action item? | - Team decide at least 2 actions needed for improvements - -
End of Week 14 | 1. What went well? | - - -
| 2. What to improve? | - - -
| 3. Action item? | - - -
End of Week 16 | 1. What went well? | - - -
| 2. What to improve? | - - -
| 3. Action item? | - - -